AI Business Operating System — Implementation Plan

Planning se Launch tak | Roman English | Draft v0.1

Project: AI Business Operating System | Status: Draft v0.1 | Language: Roman English

Note: Yeh initial planning documents hain. Market demand, API pricing, vendor eligibility aur final product decisions ko implementation se pehle validate karna hoga.

# Document Control

| Version | 0.1 — Initial research-informed draft |
| --- | --- |
| Owner | Project owner / product team |
| Review rule | Har major phase ke baad review aur approval |

# 1. Delivery Approach

Project ko small, testable milestones mein develop karna hai. Har phase ke end par demo/review aur user approval hoga.

Sequence: discover -> define requirements -> design -> build foundation -> core workflows -> AI/OCR -> test -> pilot -> launch.

Exact timeline solo developer ki availability, experience, chosen APIs aur testing feedback par depend karegi. Neeche effort ranges planning estimates hain, guarantee nahi.

# 2. Phase 0 — Problem Validation (3-5 days)

8-12 Pakistan-based small business owners/sellers se short interviews.

Unse poochna: orders kahan record karte hain, stock kaise track hota hai, daily profit kaise nikalte hain, repeat kaam kya hai, current tools ki cost aur biggest frustration kya hai.

5 common workflows observe karein; personal/customer data collect na karein unless consent ho.

Success gate: kam az kam 5 users same important problem independently mention karein aur 3-5 users prototype try karne ko tayyar hon. Ye internal validation target hai, industry benchmark nahi.

# 3. Phase 1 — Requirements and Docs (2-4 days)

PRD, TRD, App Flow, UI/UX Brief, Backend Schema aur Implementation Plan ko review karein.

Open questions decide karein: single vs multiple businesses, sales definition, stock rules, languages, OCR scope and MVP integrations.

Requirements ko Must/Should/Could/Later priority dein.

Deliverable: approved v1 docs and MVP acceptance criteria.

# 4. Phase 2 — UX Prototype (3-6 days)

Low-fidelity wireframes: onboarding, dashboard, product list/detail, add order, order detail, expense form, scan review, AI assistant and insights.

Clickable prototype banayein (e.g. Figma or another chosen design tool).

5 target users se usability test: add product, create order, find low stock, understand profit card.

Deliverable: revised navigation, screen states and UI components list.

# 5. Phase 3 — Technical Foundation (3-6 days)

Flutter project setup, linting, environments, routing and state management.

Supabase dev/staging projects, migrations, Auth and business profile.

Repository/service interfaces and error handling.

RLS policies and cross-business security tests before real business data.

Deliverable: sign-in, business setup, protected data proof.

# 6. Phase 4 — Core Business Workflows (1-2 weeks)

Products and stock movement history.

Customers and order creation/detail/status.

Transactional stock updates and cancellation restoration.

Expenses and deterministic sales/profit calculations.

Dashboard, filters, search and basic charts.

Deliverable: end-to-end business workflow works without AI.

# 7. Phase 5 — AI and OCR (4-8 days)

Build server-side AI endpoint; secure secrets and rate limits.

Add AI assistant for predefined queries using backend-derived metrics.

Add customer reply drafts and action proposal/approval flow.

Add OCR prototype for receipt images, review/edit screen and manual fallback.

Create evaluation set of representative messages/receipts (with permission and anonymized data) and measure extraction correction rate.

Deliverable: bounded AI features with usage tracking, clear errors and no silent actions.

# 8. Phase 6 — QA and Security (4-7 days)

Unit tests for calculations, repositories and services.

Widget tests for forms, loading/error/empty states and navigation.

Integration tests for create order, stock decrement, cancellation restore, expense and dashboard.

RLS tests across at least two separate test businesses.

Test slow network, API failure, duplicate submit, unreadable invoice, invalid quantity and expired session.

Review secret handling, storage access, privacy copy and account deletion flow.

Deliverable: release candidate with known issues documented.

# 9. Phase 7 — Closed Pilot (1-2 weeks)

5-10 consenting businesses ko pilot mein onboard karein.

Measure onboarding completion, time to create first order, weekly usage, OCR corrections, AI helpfulness, errors and support requests.

Interview users after 3-7 days; remove features that add complexity without clear value.

Deliverable: prioritized backlog based on observed use, not guesses.

# 10. Phase 8 — Launch and Growth

Prepare store listing, screenshots, privacy policy, terms, support contact and data deletion instructions.

Set usage limits, monitoring, backups and incident response.

Launch limited beta first; widen availability only after reliability and security checks.

Monetization experiment: free basic tier and paid AI/analytics limits; test willingness to pay before choosing exact pricing.

WhatsApp Business Platform, payment gateways and automated messaging are separate integration projects; verify current eligibility, pricing and policies before commitment.

# 11. Release Gates

Gate A: user problem validated.

Gate B: docs and MVP scope approved.

Gate C: clickable prototype passes basic usability test.

Gate D: database RLS isolation tests pass.

Gate E: core order/inventory/finance calculations pass tests.

Gate F: AI outputs validated and risky actions require approval.

Gate G: pilot feedback supports continued development.

Gate H: privacy, support and release readiness checklist complete.

# 12. Initial Backlog Priority

P0: Auth, business setup, products, orders, stock movements, expenses, dashboard calculations, RLS.

P1: AI daily summary, customer reply draft, receipt OCR and review.

P2: PDF/CSV export, push notifications, supplier management, multi-staff roles.

P3: WhatsApp Cloud API, payment integrations, forecasting and subscription billing.

# 13. Risks and Mitigations

Scope creep: MVP mein only validated essential workflows.

AI costs: per-user quotas, caching where appropriate, smaller/cheaper models for simple tasks and usage dashboard.

Bad AI answer: structured output, backend facts, validation and user feedback.

Poor OCR: editable review, supported image tips and manual entry fallback.

Security misconfiguration: RLS tests and no service-role key in client.

Low adoption: co-design with real sellers and reduce setup friction.

Third-party API changes: provider abstraction and integration tests.